AppThere Loki

Phase 1 Implementation Plan

Kernel · Skia Renderer · Headless Test Harness

Version 1.0  ·  2025

.NET 9  ·  SkiaSharp  ·  HarfBuzz  ·  Avalonia

# Table of Contents

# 1. Phase 1 Overview

Phase 1 establishes the non-negotiable foundation of AppThere Loki: the Kernel library, the Skia rendering pipeline, and the headless test harness. No UI code, no document format I/O, and no document engine are written in this phase. Every subsequent phase depends on Phase 1 being correct.

Phase 1 Exit Criteria 1. lokiprint CLI can open a static in-memory test document and render it to a valid PDF. 2. PDF output contains correct text (Latin, Arabic RTL, CJK) at the right positions. 3. PDF output contains correct geometry (rectangles, lines, images). 4. All xUnit tests pass on Windows, macOS, and Linux in CI. 5. SkiaSharp GPU surface initialises successfully on each platform (verified by a smoke test).

## 1.1 What Phase 1 Is NOT

- Not a document format reader — the test document is constructed entirely in code

- Not an Avalonia UI — no GUI is written; Avalonia is referenced but not launched

- Not a LokiKit API — that comes in Phase 2

- Not a document engine — Writer/Calc/Draw/Impress are not started

## 1.2 Deliverables

| # | Deliverable | Type | Owner project |
| --- | --- | --- | --- |
| 1 | AppThere.Loki.Kernel NuGet package | Library | AppThere.Loki.Kernel |
| 2 | AppThere.Loki.Skia NuGet package | Library | AppThere.Loki.Skia |
| 3 | lokiprint headless CLI | Executable | tools/lokiprint |
| 4 | Unit + rendering test suite | Test project | tests/unit + tests/rendering |
| 5 | CI pipeline (GitHub Actions) | Pipeline | /.github/workflows/ |
| 6 | Architecture Decision Records (ADRs) | Docs | docs/adr/ |

# 2. Repository Bootstrap

Before any code is written, the solution structure and toolchain must be established. This is a one-time task estimated at half a day.

## 2.1 Solution & Project Layout

# Create solution

dotnet new sln -n AppThere.Loki

# Kernel

dotnet new classlib -n AppThere.Loki.Kernel   -o src/Kernel/AppThere.Loki.Kernel   -f net9.0

# Skia renderer

dotnet new classlib -n AppThere.Loki.Skia     -o src/Kernel/AppThere.Loki.Skia     -f net9.0

# Headless CLI

dotnet new console  -n lokiprint              -o tools/lokiprint                   -f net9.0

# Test projects

dotnet new xunit    -n AppThere.Loki.Tests.Unit      -o tests/unit      -f net9.0

dotnet new xunit    -n AppThere.Loki.Tests.Rendering -o tests/rendering -f net9.0

# Add all to solution

dotnet sln add src/**/*.csproj tools/**/*.csproj tests/**/*.csproj

## 2.2 Directory.Build.props

A root Directory.Build.props enforces shared settings across all projects and eliminates copy-paste drift.

<Project>

<PropertyGroup>

<TargetFramework>net9.0</TargetFramework>

<Nullable>enable</Nullable>

<ImplicitUsings>enable</ImplicitUsings>

<TreatWarningsAsErrors>true</TreatWarningsAsErrors>

<Deterministic>true</Deterministic>

<LangVersion>latest</LangVersion>

</PropertyGroup>

</Project>

## 2.3 NuGet Packages (Phase 1 only)

| Package | Version | Used In | License |
| --- | --- | --- | --- |
| SkiaSharp | 2.88.x | Loki.Skia | MIT |
| SkiaSharp.HarfBuzz | 2.88.x | Loki.Skia | MIT |
| SkiaSharp.NativeAssets.Linux | 2.88.x | Loki.Skia (Linux) | MIT |
| SkiaSharp.NativeAssets.macOS | 2.88.x | Loki.Skia (macOS) | MIT |
| SkiaSharp.NativeAssets.Win32 | 2.88.x | Loki.Skia (Windows) | MIT |
| Microsoft.Extensions.Logging.Abstractions | 9.x | Loki.Kernel | MIT |
| Microsoft.Extensions.DependencyInjection | 9.x | Loki.Kernel | MIT |
| xunit | 2.9.x | tests/* | Apache-2.0 |
| xunit.runner.visualstudio | 2.8.x | tests/* | Apache-2.0 |
| Microsoft.NET.Test.Sdk | 17.x | tests/* | MIT |

# 3. AppThere.Loki.Kernel

The Kernel library contains primitives that every other project depends on. It has zero domain-specific knowledge — no documents, no rendering, no UI.

Design Rule The Kernel must compile on all target platforms (Windows, macOS, Linux, Android, iOS) with no conditional compilation. It must not reference any platform-specific API surface. It must not reference SkiaSharp — geometry types are defined independently here.

## 3.1 Geometry Primitives

Define lightweight, immutable value types. These are the units of communication between the layout engine (Phase 3+) and the renderer.

| Type | Fields | Notes |
| --- | --- | --- |
| PointF | X: float, Y: float | Logical pixel coordinate (96 dpi base) |
| SizeF | Width: float, Height: float | Logical dimensions |
| RectF | X, Y, Width, Height: float | Axis-aligned rectangle; includes helpers (Contains, Intersect, Union) |
| Thickness | Left, Top, Right, Bottom: float | Margins / padding / insets |
| Matrix3x2F | 6 floats | Affine transform; wraps System.Numerics.Matrix3x2 |
| Color | R, G, B, A: byte | 32-bit RGBA; implicit conversions to/from uint and SKColor |
| DpiScale | X: float, Y: float | HiDPI multiplier; default (1,1) |

## 3.2 Font Metadata

Kernel defines font description types only. Actual typeface loading lives in Loki.Skia.

public sealed record FontDescriptor(

string FamilyName,

FontWeight Weight  = FontWeight.Regular,

FontSlant  Slant   = FontSlant.Upright,

FontStretch Stretch = FontStretch.Normal),

float SizeInPoints = 12f);

public enum FontWeight { Thin=100, Light=300, Regular=400, Medium=500,

SemiBold=600, Bold=700, ExtraBold=800, Black=900 }

public enum FontSlant  { Upright, Italic, Oblique }

public enum FontStretch{ UltraCondensed=1, Condensed=3, Normal=5,

Expanded=7, UltraExpanded=9 }

## 3.3 Storage Abstraction

A simple IStorage interface allows the engine and export layers to read/write files without coupling to System.IO, enabling in-memory implementations for testing.

public interface IStorage

{

Task<Stream> OpenReadAsync(string path, CancellationToken ct = default);

Task<Stream> OpenWriteAsync(string path, CancellationToken ct = default);

Task<bool>   ExistsAsync(string path, CancellationToken ct = default);

IAsyncEnumerable<string> EnumerateAsync(string dir, string pattern);

}

// Implementations (both in Kernel):

public sealed class PhysicalStorage : IStorage { ... }   // System.IO

public sealed class MemoryStorage   : IStorage { ... }   // Dictionary<string,byte[]>

## 3.4 Logging

Wrap Microsoft.Extensions.Logging.ILogger behind a thin ILokiLogger interface so that consuming code does not reference MEL directly (simplifies mobile linking).

## 3.5 Image Codec Registry

Kernel defines an IImageCodec interface and a CodecRegistry. Actual codec implementations (PNG, JPEG, WebP) are registered by Loki.Skia at startup. This allows the format layer to decode images without knowing about Skia.

public interface IImageCodec

{

bool CanDecode(ReadOnlySpan<byte> header);

ImageData Decode(Stream stream);

void Encode(ImageData image, Stream output, ImageEncodeOptions opts);

}

public record ImageData(int Width, int Height, PixelFormat Format, byte[] Pixels);

# 4. AppThere.Loki.Skia

This is the heart of Phase 1. It wraps SkiaSharp and exposes a platform-neutral rendering API used identically by the UI tile consumer, headless printing, and PDF export.

## 4.1 IRenderSurface — The Output Abstraction

IRenderSurface decouples the paint pass from the specific output target. There are three implementations in Phase 1:

| Implementation | Backend | Used By |
| --- | --- | --- |
| BitmapRenderSurface | SKBitmap (CPU) | Headless tile render, test assertions |
| GpuRenderSurface | SKSurface (GL/Metal/Vulkan via Avalonia) | UI tile consumer (Phase 4) |
| PdfRenderSurface | SKDocument.CreatePdf | PDF exporter |

public interface IRenderSurface : IDisposable

{

SKCanvas Canvas { get; }

SizeF    SizeInPixels { get; }

void     Flush();

// For bitmap surfaces only:

bool     TryGetBitmap(out SKBitmap? bitmap);

}

## 4.2 ILokiPainter — The Paint API

ILokiPainter is the interface the layout/render pass uses to issue draw calls. It is implemented by LokiSkiaPainter, which translates calls to SkiaSharp. Future alternative backends (e.g. SVG canvas) implement the same interface.

public interface ILokiPainter

{

void PushTransform(Matrix3x2F transform);

void PopTransform();

void PushClip(RectF rect);

void PopClip();

void DrawRect(RectF rect, PaintStyle style);

void DrawRoundRect(RectF rect, float rx, float ry, PaintStyle style);

void DrawLine(PointF a, PointF b, LinePaint paint);

void DrawPath(LokiPath path, PaintStyle style);

void DrawImage(ImageData image, RectF dest, float opacity = 1f);

void DrawTextBlob(LokiTextBlob blob, PointF origin, TextPaint paint);

}

## 4.3 PaintStyle & TextPaint

public record PaintStyle(

Color?      Fill    = null,

Color?      Stroke  = null,

float       StrokeWidth = 1f,

DashPattern? Dash   = null,

float       Opacity = 1f);

public record TextPaint(

Color  Color,

float  Opacity = 1f);

## 4.4 Font Pipeline

### 4.4.1 IFontManager

Implemented by SkiaFontManager, which wraps SKFontManager. The interface is defined in Loki.Kernel so the engine layer can query fonts without referencing SkiaSharp.

public interface IFontManager

{

IReadOnlyList<string> GetFamilyNames();

bool TryGetTypeface(FontDescriptor desc, out ITypeface? typeface);

ITypeface GetFallback(string unicodeBlock);

void RegisterEmbedded(string resourceName);  // load from assembly

}

### 4.4.2 Bundled Fallback Fonts

The following Noto fonts are embedded as resources in AppThere.Loki.Skia and registered at startup. They guarantee that every document renders even on systems missing the required families.

| Font File | Coverage |
| --- | --- |
| NotoSans-Regular.ttf | Latin, Greek, Cyrillic, common punctuation |
| NotoSans-Bold.ttf | Bold variant of above |
| NotoSansArabic-Regular.ttf | Arabic (RTL) |
| NotoSansCJKsc-Regular.otf | Simplified Chinese, Japanese, Korean |
| NotoSerif-Regular.ttf | Serif fallback |
| NotoMono-Regular.ttf | Monospace / code |

### 4.4.3 Text Shaping — LokiTextShaper

LokiTextShaper converts a string + FontDescriptor + language tag into a LokiTextBlob (a positioned sequence of glyphs). It uses SkiaSharp.HarfBuzz for OpenType shaping and ICU (via .NET runtime) for bidirectional ordering.

public sealed class LokiTextShaper

{

// Returns a shaped, positioned glyph run

public LokiGlyphRun Shape(

ReadOnlySpan<char> text,

ITypeface typeface,

float sizeInPoints,

string? languageBcp47 = null);

// Full paragraph shaping with BiDi reordering

public LokiTextBlob ShapeParagraph(

ReadOnlySpan<char> text,

FontDescriptor baseFont,

IFontManager fonts,

float sizeInPoints,

TextDirection baseDirection = TextDirection.Auto);

}

## 4.5 Tile Renderer

The tile renderer is the core loop of Phase 1. In Phase 2 it will be called by LokiKit; in Phase 1 it is driven directly by the test harness and lokiprint CLI.

public sealed class TileRenderer

{

public TileRenderer(IFontManager fonts, IRenderSurfaceFactory surfaceFactory);

// Render a single tile from a PaintScene

public SKBitmap RenderTile(PaintScene scene, TileRequest req);

// Render all pages/parts of a scene to a PdfRenderSurface

public void RenderToPdf(PaintScene scene, Stream output, PdfRenderOptions opts);

}

PaintScene is an immutable, serialisable tree of paint commands. In Phase 1 it is constructed directly in test code. In Phase 3+ it will be produced by the layout engine.

public abstract record PaintNode;

record RectNode   (RectF Rect, PaintStyle Style) : PaintNode;

record TextNode   (string Text, PointF Origin, FontDescriptor Font,

float SizePoints, TextPaint Paint) : PaintNode;

record ImageNode  (ImageData Image, RectF Dest)     : PaintNode;

record PathNode   (LokiPath Path, PaintStyle Style)  : PaintNode;

record GroupNode  (IReadOnlyList<PaintNode> Children,

Matrix3x2F? Transform, RectF? Clip) : PaintNode;

# 5. lokiprint — Headless CLI

lokiprint is the Phase 1 integration test vehicle and the permanent headless printing tool. In Phase 1 it renders a hardcoded test scene. In Phase 7+ it opens real document files via LokiKit.

## 5.1 Phase 1 Command Interface

lokiprint test-render --output <path.pdf> [--dpi 300] [--width 595] [--height 842]

lokiprint test-render --output <path.png> --tile 0,0 [--zoom 1.0] [--dpi 150]

## 5.2 Phase 1 Test Scene

The hardcoded test scene exercises every renderer capability needed by subsequent phases. It must be hand-verified visually and pixel-hash-verified in CI.

| Section in PDF | Tests | Success Criteria |
| --- | --- | --- |
| Page background + margins | RectNode fill, page geometry | Correct A4 page size; grey margin rect visible |
| Latin body text | TextNode, basic shaping, NotoSans | Text renders at correct size, no glyph clipping |
| Bold & italic runs | Mixed font weights/slants | Correctly uses bold/italic glyphs, not synthesised |
| Arabic paragraph | RTL shaping, HarfBuzz | Right-aligned, correct glyph forms and joining |
| CJK paragraph | CJK fallback font, vertical metrics | No tofu (□) characters; correct line height |
| Nested GroupNode with clip | Transform push/pop, clip region | Content clipped to rectangle; transform correct |
| JPEG + PNG image nodes | ImageData decode + render | Images visible at correct positions and sizes |
| Path / line geometry | PathNode, LinePaint | Bezier curves and polylines render correctly |
| PDF text extraction | PDF canvas text glyphs | pdftotext extracts the Latin paragraph correctly |

## 5.3 DI Setup

lokiprint uses Microsoft.Extensions.DependencyInjection to wire its services. This pattern is reused verbatim in the LokiKit headless host in Phase 2.

var host = Host.CreateDefaultBuilder(args)

.ConfigureServices(services => {

services.AddSingleton<IStorage, PhysicalStorage>();

services.AddSingleton<IFontManager, SkiaFontManager>();

services.AddSingleton<IRenderSurfaceFactory, BitmapSurfaceFactory>();

services.AddSingleton<TileRenderer>();

services.AddSingleton<PdfRenderer>();

})

.Build();

# 6. Test Plan

All tests run in CI (no GPU required). Rendering tests use the BitmapRenderSurface CPU backend.

## 6.1 Unit Tests — AppThere.Loki.Tests.Unit

| Test Class | What It Tests | Priority |
| --- | --- | --- |
| GeometryTests | RectF.Contains, Intersect, Union; Matrix3x2F multiply | Must-Have |
| ColorTests | RGBA round-trips; SKColor conversions | Must-Have |
| MemoryStorageTests | Read/write/exists/enumerate on MemoryStorage | Must-Have |
| FontDescriptorTests | Equality, hash code, record mutations | Must-Have |
| SkiaFontManagerTests | GetFamilyNames returns non-empty; bundled fonts resolve | Must-Have |
| LokiTextShaperTests | Latin shaped run has correct glyph count; RTL run reversal | Must-Have |
| PaintStyleTests | Default values; with-expression immutability | Should-Have |
| PaintNodeTests | GroupNode child enumeration; deep clone | Should-Have |

## 6.2 Rendering Tests — AppThere.Loki.Tests.Rendering

Each rendering test builds a PaintScene, calls TileRenderer.RenderTile, and compares the result against a golden PNG stored in tests/rendering/goldens/. Golden images are generated on first run and committed to the repo.

| Test | Scene Content | Assertion |
| --- | --- | --- |
| SolidRect_Fill | Single blue RectNode | Pixel (10,10) is blue; bounding pixels are white |
| StrokedRect | RectNode with stroke only | Interior is white; border pixels match stroke color |
| LatinText_Regular | TextNode 'Hello World' NotoSans 24pt | Pixel hash matches golden; no empty rows in glyph area |
| LatinText_Bold | Same text NotoSans-Bold | Visually heavier strokes vs regular golden |
| ArabicText_RTL | TextNode Arabic string | Rightmost non-white pixel in text row < page midpoint |
| CJK_Fallback | TextNode CJK characters | No 12×12 tofu rectangles present (heuristic scan) |
| ClipGroup | GroupNode with clip rect + overflow child | Pixels outside clip rect are background color |
| TransformRotate | GroupNode with 45° rotation | Content rotated; bounds within expected range |
| ImageNode_PNG | PNG image at (0,0) | First 4×4 pixel block matches image data |
| ImageNode_JPEG | JPEG image at (100,50) | Pixel at centre of image within JPEG tolerance |
| MultipageScene_PDF | 2-page A4 scene | PDF has exactly 2 pages; file size > 5 KB |
| PdfTextExtract | Scene with Latin sentence | pdftotext output contains the sentence |

## 6.3 Smoke Tests — Platform GPU Surface

Run only on desktop CI runners (not containerised). Instantiate GpuRenderSurface without an Avalonia window (using SkiaSharp's offscreen GL surface) and verify it initialises without throwing.

# 7. CI / CD Pipeline

Phase 1 establishes the CI baseline. All subsequent phases inherit and extend it.

| Job | Runs On | Steps |
| --- | --- | --- |
| build-test-windows | windows-latest | checkout → dotnet restore → build → test (unit + rendering) |
| build-test-macos | macos-latest | checkout → dotnet restore → build → test (unit + rendering) |
| build-test-linux | ubuntu-latest | checkout → dotnet restore → build → test (unit + rendering) |
| gpu-smoke-windows | windows-latest | Only runs on main branch; instantiates GPU surface |
| gpu-smoke-macos | macos-latest | Only runs on main branch; instantiates GPU surface |
| golden-update | ubuntu-latest | Manual trigger; regenerates and commits golden PNGs |
| pack-nupkg | ubuntu-latest | Runs after all tests pass; packs Kernel + Skia as .nupkg |

Golden Image Strategy Golden PNGs are stored at tests/rendering/goldens/ and committed to the repo. The comparison allows a configurable per-pixel tolerance (default ±2 per channel) to absorb minor sub-pixel differences between OS font renderers. When a rendering change is intentional, run the golden-update CI job to regenerate and commit new goldens. The golden-update job requires a protected branch push approval to prevent accidental regressions.

# 8. Task Breakdown & Estimates

Estimates assume one senior .NET developer working full-time. Items marked 'Parallel' can be tackled by a second developer simultaneously.

## 8.1 Track A — Kernel

| # | Task | Est. Days | Priority | Parallel? |
| --- | --- | --- | --- | --- |
| A-1 | Create solution, projects, Directory.Build.props, .editorconfig | 0.5 | Day 1 | No |
| A-2 | Geometry types: PointF, SizeF, RectF, Thickness, Matrix3x2F | 0.5 | Day 1 | No |
| A-3 | Color type + SKColor implicit conversions | 0.25 | Day 1 | No |
| A-4 | DpiScale type | 0.25 | Day 1 | No |
| A-5 | IStorage + PhysicalStorage + MemoryStorage | 1.0 | Must-Have | No |
| A-6 | FontDescriptor + enums (Weight, Slant, Stretch) | 0.5 | Must-Have | Yes (after A-1) |
| A-7 | ILokiLogger + ConsoleLogger | 0.5 | Must-Have | Yes |
| A-8 | IImageCodec + ImageData + CodecRegistry | 1.0 | Must-Have | Yes (after A-5) |
| A-9 | Unit tests for A-2 through A-8 | 1.5 | Must-Have | Yes |

## 8.2 Track B — SkiaSharp Kernel Integration

| # | Task | Est. Days | Priority | Parallel? |
| --- | --- | --- | --- | --- |
| B-1 | SkiaFontManager implementing IFontManager | 1.5 | Must-Have | Yes (after A-6) |
| B-2 | Embed Noto fonts as resources; register at startup | 1.0 | Must-Have | Yes (after B-1) |
| B-3 | SkiaImageCodec: PNG + JPEG decode/encode via SkiaSharp | 1.0 | Must-Have | Yes (after A-8) |
| B-4 | LokiTextShaper: basic Latin shaping (no HarfBuzz yet) | 1.5 | Must-Have | Yes (after B-1) |
| B-5 | LokiTextShaper: HarfBuzz integration for complex scripts + RTL | 2.0 | Must-Have | After B-4 |
| B-6 | LokiTextShaper: BiDi paragraph ordering via ICU | 1.5 | Must-Have | After B-5 |
| B-7 | Unit tests for B-1 through B-6 | 2.0 | Must-Have | Yes |

## 8.3 Track C — Paint API & Surfaces

| # | Task | Est. Days | Priority | Parallel? |
| --- | --- | --- | --- | --- |
| C-1 | PaintNode record hierarchy (RectNode, TextNode, ImageNode, PathNode, GroupNode) | 1.0 | Day 1 | Yes (after A-1) |
| C-2 | PaintStyle, LinePaint, TextPaint value types | 0.5 | Day 1 | Yes (after C-1) |
| C-3 | IRenderSurface interface | 0.25 | Day 1 | Yes |
| C-4 | BitmapRenderSurface (CPU SKBitmap) | 1.0 | Must-Have | Yes (after C-3) |
| C-5 | PdfRenderSurface (SKDocument.CreatePdf) | 1.0 | Must-Have | Yes (after C-3) |
| C-6 | GpuRenderSurface stub (compiles; throws NotImplementedException) | 0.25 | Should-Have | Yes |
| C-7 | ILokiPainter interface | 0.25 | Day 1 | Yes |
| C-8 | LokiSkiaPainter: translate ILokiPainter → SKCanvas | 2.5 | Must-Have | After C-4,C-7,B-1 |
| C-9 | LokiPath type + SkiaSharp SKPath adapter | 1.0 | Must-Have | Yes (after C-7) |

## 8.4 Track D — Tile Renderer & lokiprint

| # | Task | Est. Days | Priority | Parallel? |
| --- | --- | --- | --- | --- |
| D-1 | TileRequest type; TileRenderer.RenderTile (BitmapSurface path) | 2.0 | Must-Have | After C-8, B-4 |
| D-2 | TileRenderer.RenderToPdf (PdfSurface path) | 1.5 | Must-Have | After D-1, C-5 |
| D-3 | Phase 1 test PaintScene (all 9 sections from §5.2) | 1.5 | Must-Have | After C-1 |
| D-4 | lokiprint CLI: wire DI; implement test-render subcommand | 1.0 | Must-Have | After D-1, D-2, D-3 |
| D-5 | Rendering test suite: build golden PNGs + hash comparison infra | 2.0 | Must-Have | After D-1 |
| D-6 | Rendering tests for all 12 test cases in §6.2 | 2.0 | Must-Have | After D-5 |
| D-7 | pdftotext integration test for PDF text extraction | 0.5 | Must-Have | After D-2 |

## 8.5 Track E — CI & Developer Experience

| # | Task | Est. Days | Priority | Parallel? |
| --- | --- | --- | --- | --- |
| E-1 | GitHub Actions: build-test matrix (Windows/macOS/Linux) | 1.0 | Day 1 | Yes (after A-1) |
| E-2 | Golden image update workflow + approval gate | 0.5 | Must-Have | After D-5 |
| E-3 | NuGet pack jobs for Kernel + Skia | 0.5 | Should-Have | After E-1 |
| E-4 | GPU smoke test jobs | 0.5 | Should-Have | After C-6 |
| E-5 | ADR-001: Platform font strategy | 0.5 | Must-Have | Yes |
| E-6 | ADR-002: Skia surface selection per platform | 0.5 | Must-Have | Yes |
| E-7 | ADR-003: PaintScene immutability and serialisation strategy | 0.5 | Should-Have | Yes |

## 8.6 Total Estimate

| Track | Tasks | Est. Developer-Days |
| --- | --- | --- |
| A — Kernel | 9 | 6.0 |
| B — SkiaSharp Integration | 7 | 10.5 |
| C — Paint API & Surfaces | 9 | 7.75 |
| D — Tile Renderer & lokiprint | 7 | 10.5 |
| E — CI & DevEx | 7 | 4.0 |
| TOTAL | 39 | 38.75 ≈ 8 weeks (1 dev) / 4–5 weeks (2 devs) |

# 9. Task Dependency Graph

The critical path runs A-1 → A-2 → C-1 → C-7 → C-8 → D-1 → D-2 → D-4, which is the minimum sequence required for lokiprint to emit a PDF. Everything else can be parallelised around this spine.

Critical Path Week 1: A-1 (solution setup) → A-2,A-3,A-4 (geometry) → C-1,C-2,C-3,C-7 (paint types) Week 2: A-5,A-6 (storage, fonts) → B-1 (SkiaFontManager) → B-2 (embed fonts) Week 2: (parallel) B-3 (image codec) → C-4,C-5 (bitmap + PDF surface) Week 3: B-4 (text shaping basic) → C-8 (LokiSkiaPainter) → D-3 (test scene) Week 3: (parallel) B-5,B-6 (HarfBuzz + BiDi) → D-1 (TileRenderer) Week 4: D-1 → D-2 (RenderToPdf) → D-4 (lokiprint CLI) — EXIT CRITERION REACHABLE Week 5+: D-5,D-6,D-7 (full test suite) → E-1,E-2 (CI) → polish + ADRs

# 10. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| HarfBuzz + BiDi text shaping is more complex than estimated | Medium | High | Allocate 3 extra days buffer in Track B; Latin-only fast path (B-4) unblocks CI earlier |
| SkiaSharp PDF canvas annotation API is incomplete (hyperlinks) | Medium | Low for Phase 1 | Phase 1 does not require hyperlinks; investigate in Phase 7 |
| Noto CJK font file is large (~10 MB) — slows CI download | Low | Medium | Store in Git LFS; consider variable font subset for CI only |
| GpuRenderSurface differs between platforms (GL vs Metal vs Vulkan) | High | Medium | Phase 1 only requires CPU path; GPU surface is a stub; full implementation in Phase 4 |
| .NET 9 mobile linker strips SkiaSharp native assets | Medium | High for Phase 4+ | Out of scope for Phase 1; document in ADR-002 and add linker preserve rules early |
| Golden PNG pixel hashes differ between OS font renderers | High | Medium | Use per-pixel tolerance (±2 per channel); store separate goldens per OS if needed |

# 11. Definition of Done

Phase 1 is complete when ALL of the following are true:

- lokiprint test-render --output test.pdf produces a valid PDF/A file on Windows, macOS, and Linux.

- The PDF contains readable Latin text (verified by pdftotext).

- The PDF contains readable Arabic text (verified visually and by text extraction).

- The PDF contains readable CJK text with no tofu characters.

- All 12 rendering test cases pass on all three CI platforms.

- All unit tests in AppThere.Loki.Tests.Unit pass.

- GPU surface smoke tests pass on desktop CI runners.

- No compiler warnings (TreatWarningsAsErrors is enabled).

- ADR-001, ADR-002, and ADR-003 are written and merged.

- AppThere.Loki.Kernel and AppThere.Loki.Skia are packable as .nupkg (dotnet pack succeeds).

Hand-off to Phase 2 The Phase 2 engineer receives: a working TileRenderer.RenderTile API, a PaintScene type, a PdfRenderSurface, a working IFontManager with fallback fonts, and a passing CI pipeline. Phase 2 will add ILokiDocument and the LokiKit command dispatcher on top of this foundation, replacing the hardcoded test PaintScene with a layout-engine-produced one.